## Gantt Charts
WBSID | Activity | Predecessor | DUR in Weeks | Duration in Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1.1. | Assess Requirements |  |  |  | 1: Assess Requirements
1.1.1 | Assess Requirements General consulting practice 1 (clients in manufacturing, government, IT, aerospace) | `… | 1 | Assess Requirements | 1: 1.1.1
1.1.2 | Assess Requirements General consulting practice 2 (clients in retail, healthcare, finance) | 1.1.1 | 1 | Assess Requirements | 2: 1.1.2
1.1.3 | Assess Requirements IT Planning and Implementation practice | 1.1.1 | 1 | Assess Requirements | 2: 1.1.3
1.1.4 | Assess Requirements training program practice | 1.1.1 | 1 | Assess Requirements | 2: 1.1.4
1.1.5 | Assess Requirements HR Consulting practice | 1.1.1 | 1 | Assess Requirements | 2: 1.1.5
1.1.6 | Assess Requirements Auditors | 1.1.1 | 1 | Assess Requirements | 2: 1.1.6
1.1.7 | Assess Requirements Central Administrative Staff | 1.1.1 | 1 | Assess Requirements | 2: 1.1.7
1.2. | Design |  |  |  | 3: Design
1.2.1.1 | Define Chart of Accounts structure (balance sheet and profit and loss accounts needed) | 1.1.1 - 1.1.7 | 1 | General Ledger | 3: 1.2.1.1
1.2.1.2 | Define fiscal reporting periods | 1.2.1.1 | 1 | General Ledger | 4: 1.2.1.2
1.2.1.3 | Define Chart of Accounts level of detail (subaccount roll-ups by type of expense, type of revenue, departmental source of expense, departmental source of revenue, business group source of expense, business group source of revenue) | 1.2.1.1 | 1 | General Ledger | 4: 1.2.1.3
1.2.1.4 | Assign number structure and codes to Chart of Accounts | 1.2.1.1 | 1 | General Ledger | 4: 1.2.1.4
1.2.1.5 | Define financial statement format(s) | 1.2.1.1 | 1 | General Ledger | 4: 1.2.1.5
1.2.1.6 | Review and verify starting balances | 1.2.1.1 | 1 | General Ledger | 4: 1.2.1.6
1.2.2.1 | Define format for 1099 forms | 1.2.1.1 | 1 | Accounts Payable | 4: 1.2.2.1
1.2.2.2 | Define format for invoices | 1.2.1.1 | 1 | Accounts Payable | 4: 1.2.2.2
1.2.2.3 | Identify vendor lists and types | 1.2.1.1 | 1 | Accounts Payable | 4: 1.2.2.3
1.2.2.4 | Define invoice routing pathways and invoice recipients | 1.2.2.3 | 2 | Accounts Payable | 5: 1.2.2.4; 6: 1.2.2.4
1.2.2.5 | Identify commodity codes and tax pass-through codes, match to vendors | 1.2.2.3 | 1 | Accounts Payable | 5: 1.2.2.5
1.2.2.6 | Define vendor information structure | 1.2.2.3 | 1 | Accounts Payable | 5: 1.2.2.6
1.2.2.7 | Define contractor information structure | 1.2.2.3 | 1 | Accounts Payable | 5: 1.2.2.7
1.2.3.1 | Identify employee categories for compensation groupings and leave accrual | 1.1.7 | 3 | Payroll/HR | 3: 1.2.3.1; 4: 1.2.3.1; 5: 1.2.3.1
1.2.3.2 | Identify employee categories for payment of overtime | 1.1.7 | 2 | Payroll/HR | 3: 1.2.3.2; 4: 1.2.3.2
1.2.3.3 | Define time card format and non-client time categories | 1.1.7 | 2 | Payroll/HR | 3: 1.2.3.3; 4: 1.2.3.3
1.2.3.4 | Identify pay rate structures for employee categories | 1.1.7 | 5 | Payroll/HR | 3: 1.2.3.4; 4: 1.2.3.4; 5: 1.2.3.4; 6: 1.2.3.4; 7: 1.2.3.4
1.2.3.5 | Define leave accrual system | 1.1.7 | 1 | Payroll/HR | 3: 1.2.3.5
1.2.3.6 | Define overtime rate payment structure | 1.1.7 | 1 | Payroll/HR | 3: 1.2.3.6
1.2.3.7 | Review and verify employee data | 1.2.3.1 - 1.2.3.6 | 1 | Payroll/HR | 8: 1.2.3.7
1.2.4.1 | Define activity/task markup structures | 1.2.3.7 | 1 | Job Costing/Project Accounting | 9: 1.2.4.1
1.2.4.2 | Identify OT charge process and automated source data | 1.2.3.7 | 1 | Job Costing/Project Accounting | 9: 1.2.4.2
1.2.4.3 | Identify cost billing options (% complete, actual cost, time to date) | 1.2.3.7 | 1 | Job Costing/Project Accounting | 9: 1.2.4.3
1.2.4.4 | Define project category codes needed for department/group summarization | 1.2.4.1 | 2 | Job Costing/Project Accounting | 10: 1.2.4.4; 11: 1.2.4.4
1.2.4.5 | Define project budgeting structure | 1.2.4.1 | 2 | Job Costing/Project Accounting | 10: 1.2.4.5; 11: 1.2.4.5
1.2.4.6 | Define project coding structure | 1.2.4.1 | 1 | Job Costing/Project Accounting | 10: 1.2.4.6
1.2.4.7 | Define multi-group project coding and rollup structures | 1.2.4.1 | 1 | Job Costing/Project Accounting | 10: 1.2.4.7
1.2.4.8 | Define project invoice generation process | 1.2.4.1 | 3 | Job Costing/Project Accounting | 10: 1.2.4.8; 11: 1.2.4.8; 12: 1.2.4.8
1.2.4.9 | Identify and define automated project invoice data | 1.2.4.1 | 1 | Job Costing/Project Accounting | 10: 1.2.4.9
1.2.4.10 | Identify project data input requirements – set-up and update | 1.2.4.1 | 3 | Job Costing/Project Accounting | 10: 1.2.4.10; 11: 1.2.4.10; 12: 1.2.4.10
1.3. | Develop |  |  |  | 13: Develop
1.3.1 | Modify Purchased Package | 1.2.4.10 | 3 | Develop | 13: 1.3.1; 14: 1.3.1; 15: 1.3.1
1.3.2 | Modify In-House Procedures | 1.2.4.10 | 4 | Develop | 13: 1.3.2; 14: 1.3.2; 15: 1.3.2; 16: 1.3.2
1.3.3 | Modify Manual Systems Flow | 1.2.4.10 | 3 | Develop | 13: 1.3.3; 14: 1.3.3; 15: 1.3.3
1.4. | Test |  |  |  | 16: Test
1.4.1 | Test Purchased Package | 1.3.3 | 1 | Test | 16: 1.4.1
1.4.2 | Test In-House Procedures | 1.4.1 | 2 | Test | 16: 1.4.2; 17: 1.4.2
1.4.3 | Test manual System Flows | 1.4.1 | 2 | Test | 16: 1.4.3; 17: 1.4.3
1.5. | Implement |  |  |  | 18: Implement
1.5.1 | Implement New Software Package | 1.4.2 , 1.4.3 | 2 | Implement | 18: 1.5.1; 19: 1.5.1
1.5.2 | Train Stuff | 1.5.1 | 3 | Implement | 20: 1.5.2; 21: 1.5.2; 22: 1.5.2