## W09
Cost Breakdown Structure | [7 empty] | Time Phased Budget
WBSID | Activity | Labor | Materials | Equipment | Other Direct Costs | Total |  | Week 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1.1. | Assess Requirements | 19200 | 200 | 1500 | 100 | 21000 |  | Time Phased Budget Week 1: Assess Requirements
1.1.1 | Assess Requirements General consulting practice 1 (clients in manufacturing, government, IT, aerospace) | 2800 | 100 | 0 | 0 | 2900 |  | Time Phased Budget Week 1: 2900
1.1.2 | Assess Requirements General consulting practice 2 (clients in retail, healthcare, finance) | 3200 | 0 | 1000 | 0 | 4200 |  | Time Phased Budget 2: 4200
1.1.3 | Assess Requirements IT Planning and Implementation practice | 3200 | 0 | 0 | 0 | 3200 |  | Time Phased Budget 2: 3200
1.1.4 | Assess Requirements training program practice | 3200 | 100 | 0 | 100 | 3400 |  | Time Phased Budget 2: 3400
1.1.5 | Assess Requirements HR Consulting practice | 2800 | 0 | 0 | 0 | 2800 |  | Time Phased Budget 3: 2800
1.1.6 | Assess Requirements Auditors | 3200 | 0 | 500 | 0 | 3700 |  | Time Phased Budget 3: 3700
1.1.7 | Assess Requirements Central Administrative Staff | 800 | 0 | 0 | 0 | 800 |  | Time Phased Budget 3: 800
1.2. | Design | 75600 | 3300 | 5100 | 6400 | 90400 |  | Time Phased Budget Week 1: Design
1.2.1.1 | Define Chart of Accounts structure (balance sheet and profit and loss accounts needed) | 2800 | 0 | 0 | 0 | 2800 |  | Time Phased Budget 4: 2800
1.2.1.2 | Define fiscal reporting periods | 3200 | 0 | 400 | 0 | 3600 |  | Time Phased Budget 4: 3600
1.2.1.3 | Define Chart of Accounts level of detail (subaccount roll-ups by type of expense, type of revenue, departmental source of expense, departmental source of revenue, business group source of expense, business group source of revenue) | 800 | 900 | 0 | 1000 | 2700 |  | Time Phased Budget 4: 2700
1.2.1.4 | Assign number structure and codes to Chart of Accounts | 2800 | 0 | 0 | 0 | 2800 |  | Time Phased Budget 5: 2800
1.2.1.5 | Define financial statement format(s) | 2800 | 0 | 200 | 0 | 3000 |  | Time Phased Budget 5: 3000
1.2.1.6 | Review and verify starting balances | 3200 | 0 | 0 | 0 | 3200 |  | Time Phased Budget 5: 3200
1.2.2.1 | Define format for 1099 forms | 2800 | 0 | 0 | 1500 | 4300 |  | Time Phased Budget 6: 4300
1.2.2.2 | Define format for invoices | 3200 | 800 | 0 | 0 | 4000 |  | Time Phased Budget 6: 4000
1.2.2.3 | Identify vendor lists and types | 2800 | 0 | 100 | 0 | 2900 |  | Time Phased Budget 6: 2900
1.2.2.4 | Define invoice routing pathways and invoice recipients | 3200 | 0 | 0 | 0 | 3200 |  | Time Phased Budget 7: 1600; Time Phased Budget 8: 1600
1.2.2.5 | Identify commodity codes and tax pass-through codes, match to vendors | 2800 | 0 | 0 | 300 | 3100 |  | Time Phased Budget 7: 3100
1.2.2.6 | Define vendor information structure | 3200 | 0 | 0 | 0 | 3200 |  | Time Phased Budget 8: 3200
1.2.2.7 | Define contractor information structure | 2800 | 0 | 600 | 0 | 3400 |  | Time Phased Budget 9: 3400
1.2.3.1 | Identify employee categories for compensation groupings and leave accrual | 2800 | 1000 | 0 | 2200 | 6000 |  | Time Phased Budget 9: 2000; Time Phased Budget 10: 2000; Time Phased Budget 11: 2000
1.2.3.2 | Identify employee categories for payment of overtime | 3200 | 0 | 0 | 0 | 3200 |  | Time Phased Budget 10: 1600; Time Phased Budget 11: 1600 | 24 | 25 | 26 | 27
1.2.3.3 | Define time card format and non-client time categories | 2800 | 100 | 0 | 0 | 2900 |  | Time Phased Budget 10: 1450; Time Phased Budget 11: 1450
1.2.3.4 | Identify pay rate structures for employee categories | 2800 | 0 | 0 | 0 | 2800 |  | Time Phased Budget 6: 700; Time Phased Budget 7: 700; Time Phased Budget 8: 700; Time Phased Budget 9: 700
1.2.3.5 | Define leave accrual system | 800 | 0 | 0 | 0 | 800 |  | Time Phased Budget 9: 800
1.2.3.6 | Define overtime rate payment structure | 2800 | 0 | 900 | 0 | 3700 |  | Time Phased Budget 10: 3700
1.2.3.7 | Review and verify employee data | 2800 | 0 | 0 | 0 | 2800 |  | Time Phased Budget 11: 2800
1.2.4.1 | Define activity/task markup structures | 2800 | 0 | 0 | 500 | 3300 |  | Time Phased Budget 12: 3300
1.2.4.2 | Identify OT charge process and automated source data | 800 | 0 | 700 | 0 | 1500 |  | Time Phased Budget 12: 1500
1.2.4.3 | Identify cost billing options (% complete, actual cost, time to date) | 3200 | 0 | 0 | 0 | 3200 |  | Time Phased Budget 12: 3200
1.2.4.4 | Define project category codes needed for department/group summarization | 3200 | 0 | 0 | 0 | 3200 |  | Time Phased Budget 13: 1600; Time Phased Budget 14: 1600
1.2.4.5 | Define project budgeting structure | 2800 | 0 | 0 | 0 | 2800 |  | Time Phased Budget 13: 1400; Time Phased Budget 14: 1400
1.2.4.6 | Define project coding structure | 800 | 0 | 1000 | 0 | 1800 |  | Time Phased Budget 13: 1800
1.2.4.7 | Define multi-group project coding and rollup structures | 2800 | 0 | 0 | 0 | 2800 |  | Time Phased Budget 13: 2800
1.2.4.8 | Define project invoice generation process | 3200 | 0 | 0 | 400 | 3600 |  | Time Phased Budget 15: 1200; Time Phased Budget 16: 1200; Time Phased Budget 17: 1200
1.2.4.9 | Identify and define automated project invoice data | 800 | 0 | 0 | 0 | 800 |  | Time Phased Budget 14: 800
1.2.4.10 | Identify project data input requirements – set-up and update | 800 | 500 | 1200 | 500 | 3000 |  | Time Phased Budget 15: 1000; Time Phased Budget 16: 1000; Time Phased Budget 17: 1000
1.3. | Develop | 9200 | 100 | 1500 | 900 | 11700 |  | Time Phased Budget Week 1: Develop
1.3.1 | Modify Purchased Package | 3200 | 0 | 700 | 0 | 3900 |  | Time Phased Budget 18: 1300; Time Phased Budget 19: 1300; Time Phased Budget 20: 1300
1.3.2 | Modify In-House Procedures | 2800 | 0 | 800 | 900 | 4500 |  | Time Phased Budget 18: 1125; Time Phased Budget 19: 1125; Time Phased Budget 20: 1125; Time Phased Budget 21: 1125
1.3.3 | Modify Manual Systems Flow | 3200 | 100 | 0 | 0 | 3300 |  | Time Phased Budget 18: 1100; Time Phased Budget 19: 1100; Time Phased Budget 20: 1100
1.4. | Test | 6800 | 0 | 800 | 1000 | 8600 |  | Time Phased Budget Week 1: Test
1.4.1 | Test Purchased Package | 2800 | 0 | 0 | 100 | 2900 |  | Time Phased Budget 22: 2900
1.4.2 | Test In-House Procedures | 3200 | 0 | 800 | 0 | 4000 |  | Time Phased Budget 21: 2000; Time Phased Budget 22: 2000
1.4.3 | Test manual System Flows | 800 | 0 | 0 | 900 | 1700 |  | Time Phased Budget 21: 850; Time Phased Budget 22: 850
1.5. | Implement | 6400 | 100 | 1800 | 1700 | 10000 |  | Time Phased Budget Week 1: Implement
1.5.1 | Implement New Software Package | 3200 | 0 | 800 | 0 | 4000 |  | Time Phased Budget 23: 2000
1.5.2 | Train Stuff | 3200 | 100 | 1000 | 1700 | 6000
SubTotal |  | 117200 | 3700 | 10700 | 10100 | 141700 | Totals for the Week | 2900 | 10800 | 7300 | 9100 | 9000 | 11900 | 5400 | 5500 | 6900 | 8750 | 7850 | 8000 | 7600 | 3800 | 2200 | 2200 | 2200 | 3525 | 3525 | 3525 | 3975 | 5750 | 2000
Indirect Costs (20%) |  | 23440 | 740 | 2140 | 2020 | 28340 | Cumulative Total | 2900 | 13700 | 21000 | 30100 | 39100 | 51000 | 56400 | 61900 | 68800 | 77550 | 85400 | 93400 | 101000 | 104800 | 107000 | 109200 | 111400 | 114925 | 118450 | 121975 | 125950 | 131700 | 133700
Budget Reserves (18%) |  | 21096 | 666 | 1926 | 1818 | 25506 |  | 3190 | 15070 | 23100 | 33110 | 43010 | 56100 | 62040 | 68090 | 75680 | 85305 | 93940 | 102740 | 111100 | 115280 | 117700 | 120120 | 122540 | 126417.5 | 130295 | 134172.5 | 138545 | 144870 | 147070
Management Reserve (10%) |  | 11720 | 370 | 1070 | 1010 | 14170
Total Budget |  | 173456 | 5476 | 15836 | 14948 | 209716
[8 empty] | 1 | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | 4 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 1
2000
[7 empty] | ($/hour) | [24 empty] | 2000 | 2000 | 2000
[6 empty] | Donna Donato, Controller | 100
[6 empty] | Mary Gates, Accountant | 60 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [9 empty] | 2000 | 2000 | 2000 | 2000
[6 empty] | Jan Brewer | 80 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [9 empty] | 135700 | 137700 | 139700 | 141700
[6 empty] | Kevin Hooks | 80 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 149270 | 151470 | 153670 | 155870
[6 empty] | Scott Day | 80 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[6 empty] | Jane Landsell | 80 | Time Phased Budget 15: 0.5; Time Phased Budget 16: 0.5; Time Phased Budget 17: 0.5; Time Phased Budget 18: 0.5; Time Phased Budget 19: 0.5; Time Phased Budget 20: 0.5; Time Phased Budget 21: 0.5; Time Phased Budget 22: 0.5; Time Phased Budget 23: 0.5
[6 empty] | Miriam Karpack | 80 | Time Phased Budget 15: 0.5; Time Phased Budget 16: 0.5; Time Phased Budget 17: 0.5; Time Phased Budget 18: 0.5; Time Phased Budget 19: 0.5; Time Phased Budget 20: 0.5; Time Phased Budget 21: 0.5; Time Phased Budget 22: 0.5; Time Phased Budget 23: 0.5
[6 empty] | General Administrative Staff | 20 |  | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Senior Analysts
[7 empty] | FTE | 1 | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | 4 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 1
[7 empty] | 160000 | 2800 | 6800 | 6800 | 6800 | 7600 | 7600 | 6800 | 6800 | 7600 | 7600 | 7600 | 6800 | 7600 | 6800 | 4000 | 4000 | 4000 | 7200 | 7200 | 7200 | 7200 | 7200 | 3200
[31 empty] | 1 | 1 | 1 | 1
[31 empty] | 0.5 | 0.5 | 0.5 | 0.5
[31 empty] | 0.5 | 0.5 | 0.5 | 0.5
[31 empty] | 1 | 1 | 1 | 1
[31 empty] | 3200 | 3200 | 3200 | 3200